## Summary Dashboard
HealthPulse — Healthcare Publishing Platform Feature Tracker
Dual Business: MedBrains HMS Lead Generation + Standalone Media Revenue
Sheet Name | Feature Count
Platform Core | 35
Content Types & Editor | 61
Categories & Taxonomy | 54
Author & Editorial | 29
SEO & Discovery | 32
Newsletter & Membership | 24
Social & Distribution | 21
UX & Personalization | 20
Healthcare-Specific | 27
Analytics & Monetization | 34
Admin & Operations | 26
News & Breaking Coverage | 22
Mobile App (Future) | 14
TOTAL FEATURES | 399
Phase | Description | Est. Features
MVP | Launch-ready blog with 6 core categories, articles, quick posts, SEO, medical review | ~90-100
V1.1 | Newsletter, membership, reviews, specialty verticals (7-9), editorial calendar | ~70-80
V1.2 | News vertical, live blogs, personalization, monetization, comments, buyer's guides | ~70-80
V2 | Mobile app, advanced analytics, AI features, podcasts, interactive health tools | ~80-90
Priority | Meaning
P0 | Must-have for launch — blocking
P1 | High priority — needed soon after launch
P2 | Nice to have — growth phase features
P3 | Future / aspirational
Business Model
1. MedBrains HMS Lead Generation — CTA banners, demo forms, case studies, lead attribution
2. Display Advertising — Google AdSense + direct healthcare vendor ad sales
3. Sponsored Content — native advertising, sponsor dashboards, ASCI-compliant disclosure
4. Paid Subscriptions — premium ad-free tier via Ghost membership + Stripe
5. Newsletter Sponsorships — sponsored slots in email newsletters
6. Affiliate Revenue — product review affiliate links, buyer's guide CTAs
7. Events & Webinars — co-hosted with healthcare sponsors (V2)

## Platform Core
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Homepage
Hero Section
1 | Homepage | Hero Section | Featured story hero with full-bleed image, headline, excerpt, author byline | P0 | Pending | MVP | Web | L
2 | Homepage | Hero Section | Rotating hero carousel (max 5 stories, editorial-curated) | P1 | Pending | V1.1 | Web | M
3 | Homepage | Hero Section | Breaking news takeover banner with dismiss | P1 | Pending | V1.2 | Web | M
4 | Homepage | Hero Section | Video hero variant for multimedia stories | P2 | Pending | V2 | Web | L
Storystream Feed
5 | Homepage | Storystream Feed | Editorially curated storystream feed (not algorithmic) — mixed content types | P0 | Pending | MVP | Web | L
6 | Homepage | Storystream Feed | Feed cards: thumbnail, headline, excerpt, category badge, author, timestamp | P0 | Pending | MVP | Web | M
7 | Homepage | Storystream Feed | Quick post cards (compact, no thumbnail, ~140 char preview) | P0 | Pending | MVP | Web | S
8 | Homepage | Storystream Feed | Infinite scroll with lazy loading (10 items per batch) | P0 | Pending | MVP | Web | M
9 | Homepage | Storystream Feed | Sticky category filter bar on feed (All / each category tab) | P1 | Pending | MVP | Web | M
10 | Homepage | Storystream Feed | Pinned posts — editor can pin 1-3 posts to top of feed | P1 | Pending | V1.1 | Web | S
11 | Homepage | Storystream Feed | Content type filter (articles, quick posts, reviews, guides) | P2 | Pending | V1.2 | Web | S
Sidebar / Secondary
12 | Homepage | Sidebar / Secondary | Trending stories widget (top 5 by views in 24h) | P1 | Pending | MVP | Web | M
13 | Homepage | Sidebar / Secondary | Newsletter signup widget (inline, sticky on scroll) | P0 | Pending | MVP | Web | S
14 | Homepage | Sidebar / Secondary | Popular categories widget with article counts | P2 | Pending | V1.1 | Web | S
15 | Homepage | Sidebar / Secondary | MedBrains HMS promo banner (lead-gen CTA) | P1 | Pending | MVP | Web | S | Dual business model — HMS lead generation
16 | Homepage | Sidebar / Secondary | Upcoming events / webinars widget | P2 | Pending | V1.2 | Web | M
Navigation
Header Navigation
17 | Navigation | Header Navigation | Responsive top navbar with logo, category dropdowns, search icon, user menu | P0 | Pending | MVP | Web | M
18 | Navigation | Header Navigation | Mega menu for categories — shows subcategories + featured article | P1 | Pending | V1.1 | Web | L
19 | Navigation | Header Navigation | Mobile hamburger menu with category accordion | P0 | Pending | MVP | Web | M
20 | Navigation | Header Navigation | Sticky header that hides on scroll down, shows on scroll up | P1 | Pending | MVP | Web | S
21 | Navigation | Header Navigation | Search bar expand-on-click with autocomplete suggestions | P1 | Pending | V1.1 | Web | M
Footer
22 | Navigation | Footer | Multi-column footer: categories, about, legal, social links, newsletter | P0 | Pending | MVP | Web | S
23 | Navigation | Footer | Medical disclaimer in footer (always visible) | P0 | Pending | MVP | Web | S | Regulatory requirement
24 | Navigation | Footer | Back-to-top button | P2 | Pending | V1.1 | Web | S
Search
25 | Navigation | Search | Full-text search across articles, authors, categories, tags | P0 | Pending | MVP | Web | L
26 | Navigation | Search | Search results page with filters (date, category, content type, author) | P1 | Pending | MVP | Web | M
27 | Navigation | Search | Search autocomplete / typeahead suggestions | P1 | Pending | V1.1 | Web | M
28 | Navigation | Search | Search analytics — track popular queries, zero-result queries | P2 | Pending | V1.2 | Web | M
Mobile & PWA
Responsive Design
29 | Mobile & PWA | Responsive Design | Fully responsive layout (mobile-first, 320px to 4K) | P0 | Pending | MVP | Web | L
30 | Mobile & PWA | Responsive Design | Touch-optimized interactions (swipe, tap targets ≥44px) | P0 | Pending | MVP | Web | M
31 | Mobile & PWA | Responsive Design | Adaptive images (srcset, WebP/AVIF with fallback) | P0 | Pending | MVP | Web | M
32 | Mobile & PWA | Responsive Design | Mobile-specific reading mode (minimal chrome, max content) | P1 | Pending | V1.1 | Web | M
PWA
33 | Mobile & PWA | PWA | Service worker for offline reading of cached articles | P2 | Pending | V1.2 | Web | L
34 | Mobile & PWA | PWA | Add-to-homescreen prompt | P2 | Pending | V1.2 | Web | S
35 | Mobile & PWA | PWA | Web push notifications for breaking news / newsletter | P2 | Pending | V1.2 | Web | M

## Content Types & Editor
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Quick Posts (Micro-Blog)
Quick Post Creation
1 | Quick Posts (Micro-Blog) | Quick Post Creation | Quick post editor — plain text + markdown, max 500 words, minimal UI | P0 | Pending | MVP | Web | M
2 | Quick Posts (Micro-Blog) | Quick Post Creation | Optional single image/embed attachment | P0 | Pending | MVP | Web | S
3 | Quick Posts (Micro-Blog) | Quick Post Creation | Category and tag selection (quick select chips) | P0 | Pending | MVP | Web | S
4 | Quick Posts (Micro-Blog) | Quick Post Creation | One-click publish (skip full editorial workflow for quick posts) | P0 | Pending | MVP | Web | S
5 | Quick Posts (Micro-Blog) | Quick Post Creation | Source URL field — link to external article being commented on | P0 | Pending | MVP | Web | S
6 | Quick Posts (Micro-Blog) | Quick Post Creation | Quick post thread — chain multiple quick posts into a thread | P2 | Pending | V1.2 | Web | M
Quick Post Display
7 | Quick Posts (Micro-Blog) | Quick Post Display | Compact card layout in feed (no hero image, inline text preview) | P0 | Pending | MVP | Web | S
8 | Quick Posts (Micro-Blog) | Quick Post Display | Expand-in-place reading (no page navigation needed) | P1 | Pending | V1.1 | Web | M
9 | Quick Posts (Micro-Blog) | Quick Post Display | Share buttons (Twitter/X, LinkedIn, WhatsApp, copy link) | P0 | Pending | MVP | Web | S
Long-Form Articles
Rich Text Editor
10 | Long-Form Articles | Rich Text Editor | WYSIWYG editor with heading levels, bold, italic, lists, blockquotes | P0 | Pending | MVP | Web | L | Ghost editor or custom
11 | Long-Form Articles | Rich Text Editor | Inline image insertion with caption, alt text, credit | P0 | Pending | MVP | Web | M
12 | Long-Form Articles | Rich Text Editor | Embed support: YouTube, Twitter, Instagram, CodePen, PubMed | P0 | Pending | MVP | Web | M
13 | Long-Form Articles | Rich Text Editor | Table insertion and editing | P1 | Pending | V1.1 | Web | M
14 | Long-Form Articles | Rich Text Editor | Custom callout/alert boxes (info, warning, expert opinion, key takeaway) | P1 | Pending | MVP | Web | M
15 | Long-Form Articles | Rich Text Editor | Footnotes / endnotes with reference linking | P1 | Pending | V1.1 | Web | M
16 | Long-Form Articles | Rich Text Editor | Inline citation insertion — link to PubMed, DOI, clinical study | P0 | Pending | MVP | Web | M | Healthcare credibility essential
17 | Long-Form Articles | Rich Text Editor | Code snippet embedding (for healthtech/dev articles) | P2 | Pending | V1.2 | Web | S
18 | Long-Form Articles | Rich Text Editor | Markdown mode toggle (switch between WYSIWYG and raw markdown) | P2 | Pending | V1.1 | Web | M
Article Display
19 | Long-Form Articles | Article Display | Full-width hero image with gradient text overlay | P0 | Pending | MVP | Web | M
20 | Long-Form Articles | Article Display | Author byline with avatar, name, credentials, follow button | P0 | Pending | MVP | Web | S
21 | Long-Form Articles | Article Display | Medical reviewer badge — reviewed by Dr. X, MD (with date) | P0 | Pending | MVP | Web | S | E-E-A-T compliance for Google YMYL
22 | Long-Form Articles | Article Display | Dual timestamp: Published date + Last medically reviewed date | P0 | Pending | MVP | Web | S
23 | Long-Form Articles | Article Display | Reading time estimate (words/200 wpm) | P0 | Pending | MVP | Web | S
24 | Long-Form Articles | Article Display | Auto-generated table of contents (from H2/H3 headings) | P1 | Pending | MVP | Web | M
25 | Long-Form Articles | Article Display | Reading progress bar (sticky top) | P1 | Pending | V1.1 | Web | S
26 | Long-Form Articles | Article Display | Related articles section (3-4 cards, same category/tags) | P1 | Pending | MVP | Web | M
27 | Long-Form Articles | Article Display | Medical disclaimer banner per article (contextual based on category) | P0 | Pending | MVP | Web | S | Legal requirement for patient-facing content
28 | Long-Form Articles | Article Display | Source citations section at article bottom (numbered references) | P0 | Pending | MVP | Web | M
29 | Long-Form Articles | Article Display | Print-friendly view / save as PDF | P2 | Pending | V1.2 | Web | M
Reviews & Buyer's Guides
Reviews
30 | Reviews & Buyer's Guides | Reviews | Review scoring system (0-10 with half-points) per criteria | P1 | Pending | V1.1 | Web | M
31 | Reviews & Buyer's Guides | Reviews | Scorecard component — overall score + category scores (features, value, support, ease) | P1 | Pending | V1.1 | Web | M
32 | Reviews & Buyer's Guides | Reviews | Pros/cons structured section | P1 | Pending | V1.1 | Web | S
33 | Reviews & Buyer's Guides | Reviews | Product spec table (structured data for comparison) | P1 | Pending | V1.1 | Web | M
34 | Reviews & Buyer's Guides | Reviews | Verdict badge (Editor's Choice, Best Value, Best for Small Hospitals) | P1 | Pending | V1.1 | Web | S
35 | Reviews & Buyer's Guides | Reviews | Conflict of interest / sponsorship disclosure on reviews | P0 | Pending | V1.1 | Web | S | Trust & transparency
36 | Reviews & Buyer's Guides | Reviews | Review categories: HMS software, medical devices, health apps, EHR systems | P1 | Pending | V1.1 | Web | S
Buyer's Guides
37 | Reviews & Buyer's Guides | Buyer's Guides | Multi-product comparison table (side-by-side specs + scores) | P2 | Pending | V1.2 | Web | L
38 | Reviews & Buyer's Guides | Buyer's Guides | Product recommendation engine (by hospital size, budget, specialty) | P2 | Pending | V2 | Web | XL
39 | Reviews & Buyer's Guides | Buyer's Guides | Affiliate/CTA links per product (tracked for monetization) | P2 | Pending | V1.2 | Web | M | Revenue stream
40 | Reviews & Buyer's Guides | Buyer's Guides | Last updated date with auto-stale warning (>6 months) | P2 | Pending | V1.2 | Web | S
Live Blogs
Live Blog Engine
41 | Live Blogs | Live Blog Engine | Live blog page — reverse-chron updates with timestamps | P2 | Pending | V1.2 | Web | L
42 | Live Blogs | Live Blog Engine | Real-time auto-refresh (new updates appear without page reload) | P2 | Pending | V1.2 | Web | M
43 | Live Blogs | Live Blog Engine | Pinned key update at top of live blog | P2 | Pending | V1.2 | Web | S
44 | Live Blogs | Live Blog Engine | Multi-author live blog (different reporters can post updates) | P2 | Pending | V1.2 | Web | M
45 | Live Blogs | Live Blog Engine | Embed tweets, images, videos inline in live updates | P2 | Pending | V1.2 | Web | M
46 | Live Blogs | Live Blog Engine | Use cases: HIMSS live coverage, Union Budget health analysis, NMC updates | P2 | Pending | V1.2 | Web | S | Key differentiator for news coverage
Multimedia Content
Video
47 | Multimedia Content | Video | Video embed support (YouTube, Vimeo, custom player) | P1 | Pending | MVP | Web | M
48 | Multimedia Content | Video | Video-first article template (video hero + transcript below) | P2 | Pending | V1.2 | Web | M
49 | Multimedia Content | Video | Video series / playlists grouped by topic | P2 | Pending | V2 | Web | M
Podcast
50 | Multimedia Content | Podcast | Podcast player embed (inline audio player with show notes) | P2 | Pending | V1.2 | Web | M
51 | Multimedia Content | Podcast | Podcast series page with episode list and RSS feed | P2 | Pending | V2 | Web | M
52 | Multimedia Content | Podcast | Transcript auto-display below podcast player | P2 | Pending | V2 | Web | M
Visual Content
53 | Multimedia Content | Visual Content | Image gallery component (lightbox, swipe on mobile) | P1 | Pending | V1.1 | Web | M
54 | Multimedia Content | Visual Content | Infographic full-width display with zoom | P1 | Pending | V1.1 | Web | M
55 | Multimedia Content | Visual Content | Interactive data visualization embeds (charts, maps) | P2 | Pending | V2 | Web | L
56 | Multimedia Content | Visual Content | Before/after image slider (for medical device comparisons) | P2 | Pending | V2 | Web | M
Case Studies
Case Study Template
57 | Case Studies | Case Study Template | Structured case study template: challenge, solution, results, metrics | P1 | Pending | V1.1 | Web | M
58 | Case Studies | Case Study Template | Key metrics highlight boxes (e.g., 30% reduction in wait time) | P1 | Pending | V1.1 | Web | S
59 | Case Studies | Case Study Template | Hospital/organization profile sidebar in case studies | P2 | Pending | V1.2 | Web | M
60 | Case Studies | Case Study Template | Case study gallery page with filter by hospital type/size/solution | P2 | Pending | V1.2 | Web | M
61 | Case Studies | Case Study Template | MedBrains HMS case study integration — link to demo request | P1 | Pending | V1.1 | Web | S | HMS lead generation

## Categories & Taxonomy
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Category System Architecture
Core Category Infrastructure
1 | Category System Architecture | Core Category Infrastructure | Hierarchical category system: parent category → subcategories → tags | P0 | Pending | MVP | Web | L
2 | Category System Architecture | Core Category Infrastructure | Category page template: header, description, featured post, feed | P0 | Pending | MVP | Web | M
3 | Category System Architecture | Core Category Infrastructure | Subcategory landing pages with filtered feed | P1 | Pending | V1.1 | Web | M
4 | Category System Architecture | Core Category Infrastructure | Category-specific color coding and icons throughout UI | P1 | Pending | MVP | Web | S
5 | Category System Architecture | Core Category Infrastructure | Category badges on all content cards and article pages | P0 | Pending | MVP | Web | S
6 | Category System Architecture | Core Category Infrastructure | Multi-category assignment (article can belong to 1 primary + secondary categories) | P1 | Pending | V1.1 | Web | M
7 | Category System Architecture | Core Category Infrastructure | Category RSS feed (per-category syndication) | P1 | Pending | V1.1 | Web | S
8 | Category System Architecture | Core Category Infrastructure | Category newsletter segment (auto-send to subscribers of that category) | P1 | Pending | V1.1 | Web | M
9 | Category System Architecture | Core Category Infrastructure | Admin: create/edit/archive categories without code changes | P0 | Pending | MVP | Web | M | Scalable — new verticals via admin panel
Tag System
10 | Category System Architecture | Tag System | Free-form tag creation by editors (with suggested existing tags) | P0 | Pending | MVP | Web | M
11 | Category System Architecture | Tag System | Tag page with all content tagged with that term | P0 | Pending | MVP | Web | S
12 | Category System Architecture | Tag System | Tag cloud / popular tags widget | P2 | Pending | V1.2 | Web | S
13 | Category System Architecture | Tag System | Tag merge/rename tool for editorial cleanup | P2 | Pending | V1.2 | Web | M
14 | Category System Architecture | Tag System | Auto-suggested tags based on article content (AI-assisted) | P2 | Pending | V2 | Web | L
Core Categories (Launch)
Hospital Leadership & Strategy
15 | Core Categories (Launch) | Hospital Leadership & Strategy | Category: Hospital Leadership & Strategy — CEO/CMO/admin audience | P0 | Pending | MVP | Web | S
16 | Core Categories (Launch) | Hospital Leadership & Strategy | Subcategories: Strategic Planning, Financial Management, Quality Accreditation, Governance | P1 | Pending | MVP | Web | S
17 | Core Categories (Launch) | Hospital Leadership & Strategy | Content types: opinion pieces, case studies, interviews, data analysis | P0 | Pending | MVP | Web | S
Patient Education & Wellness
18 | Core Categories (Launch) | Patient Education & Wellness | Category: Patient Education & Wellness — patient/family audience | P0 | Pending | MVP | Web | S
19 | Core Categories (Launch) | Patient Education & Wellness | Subcategories: Disease Guides, Wellness Tips, Nutrition, Mental Health, Pregnancy | P1 | Pending | MVP | Web | S
20 | Core Categories (Launch) | Patient Education & Wellness | Enhanced medical review requirement (all patient content must be reviewed) | P0 | Pending | MVP | Web | M | Mandatory for YMYL compliance
21 | Core Categories (Launch) | Patient Education & Wellness | Readability score enforcement (Flesch-Kincaid ≤ 8th grade for patient content) | P1 | Pending | V1.1 | Web | M
Doctor & Clinical Excellence
22 | Core Categories (Launch) | Doctor & Clinical Excellence | Category: Doctor & Clinical Excellence — physician/nurse audience | P0 | Pending | MVP | Web | S
23 | Core Categories (Launch) | Doctor & Clinical Excellence | Subcategories: Clinical Guidelines, Case Reports, Research Updates, CME | P1 | Pending | MVP | Web | S
24 | Core Categories (Launch) | Doctor & Clinical Excellence | Content types: clinical pearls, evidence summaries, expert opinions | P0 | Pending | MVP | Web | S
Operations & Efficiency
25 | Core Categories (Launch) | Operations & Efficiency | Category: Operations & Efficiency — hospital manager/dept head audience | P0 | Pending | MVP | Web | S
26 | Core Categories (Launch) | Operations & Efficiency | Subcategories: Process Improvement, Supply Chain, Facility Management, Staffing | P1 | Pending | MVP | Web | S
27 | Core Categories (Launch) | Operations & Efficiency | Content types: how-to guides, checklists, templates, benchmarking data | P0 | Pending | MVP | Web | S
Technology & Innovation
28 | Core Categories (Launch) | Technology & Innovation | Category: Technology & Innovation — CIO/IT/healthtech audience | P0 | Pending | MVP | Web | S
29 | Core Categories (Launch) | Technology & Innovation | Subcategories: AI in Healthcare, EHR/EMR, Telemedicine, Cybersecurity, Interoperability | P1 | Pending | MVP | Web | S
30 | Core Categories (Launch) | Technology & Innovation | Product review integration (link to Reviews content type) | P1 | Pending | V1.1 | Web | S
Regulatory & Compliance
31 | Core Categories (Launch) | Regulatory & Compliance | Category: Regulatory & Compliance — compliance officer/legal audience | P0 | Pending | MVP | Web | S
32 | Core Categories (Launch) | Regulatory & Compliance | Subcategories: NABH/JCI, NMC Updates, Legal Rulings, Data Privacy, DPDP Act | P1 | Pending | MVP | Web | S
33 | Core Categories (Launch) | Regulatory & Compliance | Regulatory alert badges on time-sensitive compliance content | P1 | Pending | V1.1 | Web | S
Specialty Verticals (Growth Phase)
Nursing & Allied Health
34 | Specialty Verticals (Growth Phase) | Nursing & Allied Health | Category: Nursing & Allied Health — nurses, physios, technicians | P1 | Pending | V1.1 | Web | S
35 | Specialty Verticals (Growth Phase) | Nursing & Allied Health | Subcategories: Nursing Practice, Physiotherapy, Lab Tech, Radiology Tech | P1 | Pending | V1.1 | Web | S
Pharma Industry
36 | Specialty Verticals (Growth Phase) | Pharma Industry | Category: Pharma Industry — pharma companies, distributors | P1 | Pending | V1.1 | Web | S
37 | Specialty Verticals (Growth Phase) | Pharma Industry | Subcategories: Drug Launches, Pricing & Policy, Supply Chain, R&D Pipeline | P1 | Pending | V1.1 | Web | S
Medical Devices & Equipment
38 | Specialty Verticals (Growth Phase) | Medical Devices & Equipment | Category: Medical Devices & Equipment — manufacturers, biomedical engineers | P1 | Pending | V1.1 | Web | S
39 | Specialty Verticals (Growth Phase) | Medical Devices & Equipment | Subcategories: Device Reviews, Procurement Guides, Regulatory Approvals, Innovation | P1 | Pending | V1.1 | Web | S
Health Insurance & TPA
40 | Specialty Verticals (Growth Phase) | Health Insurance & TPA | Category: Health Insurance & TPA — insurers, TPA executives, brokers | P2 | Pending | V1.2 | Web | S
41 | Specialty Verticals (Growth Phase) | Health Insurance & TPA | Subcategories: Policy Analysis, Claim Trends, Regulatory Changes, Product Reviews | P2 | Pending | V1.2 | Web | S
HealthTech & Startups
42 | Specialty Verticals (Growth Phase) | HealthTech & Startups | Category: HealthTech & Startups — founders, investors, digital health builders | P2 | Pending | V1.2 | Web | S
43 | Specialty Verticals (Growth Phase) | HealthTech & Startups | Subcategories: Funding News, Product Launches, Founder Interviews, Market Analysis | P2 | Pending | V1.2 | Web | S
Medical Education & Research
44 | Specialty Verticals (Growth Phase) | Medical Education & Research | Category: Medical Education & Research — students, academics, researchers | P2 | Pending | V1.2 | Web | S
45 | Specialty Verticals (Growth Phase) | Medical Education & Research | Subcategories: NEET/USMLE, Residency, Research Methods, Conference Reports | P2 | Pending | V1.2 | Web | S
Content Discovery
Topic Pages
46 | Content Discovery | Topic Pages | Auto-generated topic pages from frequently used tags | P1 | Pending | V1.1 | Web | M
47 | Content Discovery | Topic Pages | Curated topic hub pages (e.g., 'AI in Healthcare' with intro + curated list) | P2 | Pending | V1.2 | Web | L
48 | Content Discovery | Topic Pages | Topic following — users can follow specific topics for personalized feed | P2 | Pending | V1.2 | Web | M
Content Series & Collections
49 | Content Discovery | Content Series & Collections | Content series — multi-part articles linked sequentially (Part 1, 2, 3...) | P1 | Pending | V1.1 | Web | M
50 | Content Discovery | Content Series & Collections | Editorial collections — curated bundles of related articles | P2 | Pending | V1.2 | Web | M
51 | Content Discovery | Content Series & Collections | Series navigation component (prev/next within series) | P1 | Pending | V1.1 | Web | S
Related Content Engine
52 | Content Discovery | Related Content Engine | Related articles algorithm (based on category + tags + recency) | P1 | Pending | MVP | Web | M
53 | Content Discovery | Related Content Engine | "More from this author" section on article pages | P1 | Pending | V1.1 | Web | S
54 | Content Discovery | Related Content Engine | "Readers also liked" section (based on reading patterns) | P2 | Pending | V2 | Web | L

## Author & Editorial
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Author Profiles
Author Page
1 | Author Profiles | Author Page | Public author profile page: photo, bio, credentials, social links | P0 | Pending | MVP | Web | M
2 | Author Profiles | Author Page | Author credential display: MD, MBBS, PhD, board certifications | P0 | Pending | MVP | Web | S | E-E-A-T compliance
3 | Author Profiles | Author Page | ORCID integration — link to research publications | P2 | Pending | V1.2 | Web | S
4 | Author Profiles | Author Page | Author article feed (all content by this author) | P0 | Pending | MVP | Web | S
5 | Author Profiles | Author Page | Follow author button + follower count | P1 | Pending | V1.1 | Web | M
6 | Author Profiles | Author Page | Author expertise tags (cardiology, health policy, digital health, etc.) | P1 | Pending | MVP | Web | S
7 | Author Profiles | Author Page | Conflict of interest / disclosure statement on author profile | P0 | Pending | MVP | Web | S | Transparency requirement
Author Types
8 | Author Profiles | Author Types | Staff writer profiles (full-time editorial team) | P0 | Pending | MVP | Web | S
9 | Author Profiles | Author Types | Guest contributor profiles (external experts, doctors) | P0 | Pending | MVP | Web | S
10 | Author Profiles | Author Types | Medical reviewer profiles (separate role — reviews but doesn't write) | P0 | Pending | MVP | Web | S
11 | Author Profiles | Author Types | Multi-author articles (co-authored, each author bylined) | P1 | Pending | V1.1 | Web | M
12 | Author Profiles | Author Types | Editorial board page — list of all medical reviewers and advisors | P1 | Pending | V1.1 | Web | S
Editorial Workflow
Content Pipeline
13 | Editorial Workflow | Content Pipeline | Article status workflow: Draft → In Review → Medical Review → Editor Approval → Scheduled → Published | P0 | Pending | MVP | Web | L
14 | Editorial Workflow | Content Pipeline | Assign reviewer / editor to article | P0 | Pending | MVP | Web | M
15 | Editorial Workflow | Content Pipeline | Inline comments / suggestions on draft (like Google Docs) | P1 | Pending | V1.1 | Web | L
16 | Editorial Workflow | Content Pipeline | Revision history — full diff between versions | P1 | Pending | V1.1 | Web | M
17 | Editorial Workflow | Content Pipeline | Quick post simplified workflow: Draft → Published (editor bypass for senior writers) | P0 | Pending | MVP | Web | S
18 | Editorial Workflow | Content Pipeline | Content scheduling — publish at specific date/time | P0 | Pending | MVP | Web | M
19 | Editorial Workflow | Content Pipeline | Embargo support — article exists but hidden until embargo lifts | P2 | Pending | V1.2 | Web | M
Medical Review Process
20 | Editorial Workflow | Medical Review Process | Medical review assignment — route article to qualified reviewer by specialty | P0 | Pending | MVP | Web | M
21 | Editorial Workflow | Medical Review Process | Medical review checklist — factual accuracy, source verification, bias check | P0 | Pending | MVP | Web | M
22 | Editorial Workflow | Medical Review Process | Medical review badge auto-applied after approval | P0 | Pending | MVP | Web | S
23 | Editorial Workflow | Medical Review Process | Review expiry — flag articles needing re-review after 12 months | P1 | Pending | V1.1 | Web | M
24 | Editorial Workflow | Medical Review Process | Category-based review rules (patient content = mandatory, tech news = optional) | P1 | Pending | V1.1 | Web | M
Editorial Calendar
25 | Editorial Workflow | Editorial Calendar | Calendar view of scheduled content (month/week view) | P1 | Pending | V1.1 | Web | L
26 | Editorial Workflow | Editorial Calendar | Drag-and-drop scheduling on calendar | P2 | Pending | V1.2 | Web | M
27 | Editorial Workflow | Editorial Calendar | Category distribution view — ensure balanced coverage across categories | P2 | Pending | V1.2 | Web | M
28 | Editorial Workflow | Editorial Calendar | Health awareness days integration (World Heart Day, etc.) — suggested content | P2 | Pending | V1.2 | Web | M
29 | Editorial Workflow | Editorial Calendar | Planned vs published tracking | P1 | Pending | V1.1 | Web | S

## SEO & Discovery
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Technical SEO
Schema Markup
1 | Technical SEO | Schema Markup | Schema.org Article markup on all articles (headline, author, datePublished) | P0 | Pending | MVP | Web | M
2 | Technical SEO | Schema Markup | Schema.org MedicalWebPage markup on patient education content | P0 | Pending | MVP | Web | M | Critical for Google YMYL trust signals
3 | Technical SEO | Schema Markup | Schema.org Person markup for authors (name, credentials, sameAs links) | P0 | Pending | MVP | Web | S
4 | Technical SEO | Schema Markup | Schema.org FAQPage markup on FAQ-style articles | P1 | Pending | V1.1 | Web | S
5 | Technical SEO | Schema Markup | Schema.org Review markup on review content (aggregateRating) | P1 | Pending | V1.1 | Web | S
6 | Technical SEO | Schema Markup | Schema.org BreadcrumbList for navigation trail | P0 | Pending | MVP | Web | S
7 | Technical SEO | Schema Markup | Schema.org Organization markup on about page | P0 | Pending | MVP | Web | S
8 | Technical SEO | Schema Markup | JSON-LD injection (not microdata) for all schema | P0 | Pending | MVP | Web | S
Meta & Crawlability
9 | Technical SEO | Meta & Crawlability | Auto-generated meta title + description with manual override | P0 | Pending | MVP | Web | M
10 | Technical SEO | Meta & Crawlability | Canonical URL on every page (prevent duplicate content) | P0 | Pending | MVP | Web | S
11 | Technical SEO | Meta & Crawlability | XML sitemap auto-generation (articles, categories, authors, tags) | P0 | Pending | MVP | Web | M
12 | Technical SEO | Meta & Crawlability | robots.txt configuration | P0 | Pending | MVP | Web | S
13 | Technical SEO | Meta & Crawlability | Open Graph meta tags (og:title, og:description, og:image) | P0 | Pending | MVP | Web | S
14 | Technical SEO | Meta & Crawlability | Twitter Card meta tags (summary_large_image) | P0 | Pending | MVP | Web | S
15 | Technical SEO | Meta & Crawlability | hreflang tags for future multilingual support (Hindi, regional) | P2 | Pending | V2 | Web | M
16 | Technical SEO | Meta & Crawlability | Structured URL patterns: /category/subcategory/article-slug | P0 | Pending | MVP | Web | S
17 | Technical SEO | Meta & Crawlability | 301 redirect management for URL changes | P1 | Pending | V1.1 | Web | M
Performance
18 | Technical SEO | Performance | Core Web Vitals optimization — LCP < 2.5s, FID < 100ms, CLS < 0.1 | P0 | Pending | MVP | Web | L | Google ranking factor
19 | Technical SEO | Performance | Static site generation (SSG) for articles via Astro | P0 | Pending | MVP | Web | L
20 | Technical SEO | Performance | Image optimization pipeline (WebP/AVIF, lazy loading, responsive srcset) | P0 | Pending | MVP | Web | M
21 | Technical SEO | Performance | CDN caching (Cloudflare) with cache-busting on content updates | P0 | Pending | MVP | Web | M
22 | Technical SEO | Performance | Lighthouse CI — automated score tracking in deploys | P1 | Pending | V1.1 | Web | M
23 | Technical SEO | Performance | Critical CSS inlining for above-the-fold content | P1 | Pending | V1.1 | Web | M
Content SEO
SEO Tools for Writers
24 | Content SEO | SEO Tools for Writers | SEO preview panel in editor (Google snippet preview, char counts) | P1 | Pending | V1.1 | Web | M
25 | Content SEO | SEO Tools for Writers | Focus keyword field with density indicator | P1 | Pending | V1.1 | Web | M
26 | Content SEO | SEO Tools for Writers | Internal linking suggestions (suggest related published articles while writing) | P1 | Pending | V1.1 | Web | L
27 | Content SEO | SEO Tools for Writers | Readability score (Flesch-Kincaid) displayed in editor | P1 | Pending | V1.1 | Web | M
28 | Content SEO | SEO Tools for Writers | Alt text enforcement — warn if images missing alt text | P0 | Pending | MVP | Web | S
29 | Content SEO | SEO Tools for Writers | Heading structure validator (H1 → H2 → H3, no skips) | P1 | Pending | V1.1 | Web | S
Internal Linking
30 | Content SEO | Internal Linking | Auto-suggest internal links based on content similarity | P2 | Pending | V1.2 | Web | L
31 | Content SEO | Internal Linking | Orphan content report (articles with no internal links pointing to them) | P2 | Pending | V1.2 | Web | M
32 | Content SEO | Internal Linking | Broken link checker (scan all internal links weekly) | P2 | Pending | V1.2 | Web | M

## Newsletter & Membership
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Newsletter System
Newsletter Core
1 | Newsletter System | Newsletter Core | Email newsletter signup form (name, email, preference checkboxes) | P0 | Pending | MVP | Web | M
2 | Newsletter System | Newsletter Core | Double opt-in confirmation email | P0 | Pending | MVP | Web | S
3 | Newsletter System | Newsletter Core | One-click unsubscribe (CAN-SPAM/GDPR compliant) | P0 | Pending | MVP | Web | S
4 | Newsletter System | Newsletter Core | Newsletter preference center (select categories, frequency) | P1 | Pending | V1.1 | Web | M
5 | Newsletter System | Newsletter Core | Welcome email sequence (3-part onboarding drip) | P1 | Pending | V1.1 | Web | M
6 | Newsletter System | Newsletter Core | Ghost built-in newsletter (free tier, no extra cost) | P0 | Pending | MVP | Web | S | Ghost CMS includes newsletter features
Newsletter Types
7 | Newsletter System | Newsletter Types | Daily digest — top 5 stories across all categories | P1 | Pending | V1.1 | Web | M
8 | Newsletter System | Newsletter Types | Weekly category newsletters (one per active category) | P1 | Pending | V1.1 | Web | M
9 | Newsletter System | Newsletter Types | Breaking news alert email (manual trigger for urgent stories) | P1 | Pending | V1.2 | Web | M
10 | Newsletter System | Newsletter Types | Monthly roundup — best of the month, editor picks | P2 | Pending | V1.2 | Web | M
11 | Newsletter System | Newsletter Types | Personalized newsletter — AI-selected based on reading history | P2 | Pending | V2 | Web | XL
Newsletter Analytics
12 | Newsletter System | Newsletter Analytics | Open rate, click rate, unsubscribe rate per newsletter | P1 | Pending | V1.1 | Web | M
13 | Newsletter System | Newsletter Analytics | Top clicked links per newsletter issue | P1 | Pending | V1.1 | Web | S
14 | Newsletter System | Newsletter Analytics | Subscriber growth chart (daily/weekly/monthly) | P1 | Pending | V1.1 | Web | M
15 | Newsletter System | Newsletter Analytics | Segment performance comparison | P2 | Pending | V1.2 | Web | M
Membership & Access Tiers
Tier Structure
16 | Membership & Access Tiers | Tier Structure | Free tier — all content accessible, ad-supported | P0 | Pending | MVP | Web | S
17 | Membership & Access Tiers | Tier Structure | Registered tier — free account for bookmarks, following, comments | P1 | Pending | V1.1 | Web | M
18 | Membership & Access Tiers | Tier Structure | Premium tier — ad-free, exclusive content, early access | P2 | Pending | V1.2 | Web | L
19 | Membership & Access Tiers | Tier Structure | Stripe integration for paid subscriptions | P2 | Pending | V1.2 | Web | L
20 | Membership & Access Tiers | Tier Structure | Ghost membership system (built-in free/paid tiers) | P2 | Pending | V1.2 | Web | M | Ghost has built-in Stripe integration
User Accounts
21 | Membership & Access Tiers | User Accounts | Email/password registration | P1 | Pending | V1.1 | Web | M
22 | Membership & Access Tiers | User Accounts | Google OAuth login | P1 | Pending | V1.1 | Web | M
23 | Membership & Access Tiers | User Accounts | User profile page (name, photo, bio, followed topics/authors) | P1 | Pending | V1.1 | Web | M
24 | Membership & Access Tiers | User Accounts | Account settings (email preferences, password change, delete account) | P1 | Pending | V1.1 | Web | M

## Social & Distribution
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Social Sharing
Share Functionality
1 | Social Sharing | Share Functionality | Share buttons on every article: Twitter/X, LinkedIn, Facebook, WhatsApp, copy link | P0 | Pending | MVP | Web | S
2 | Social Sharing | Share Functionality | WhatsApp share with pre-formatted message (title + excerpt + URL) | P0 | Pending | MVP | Web | S | Critical for Indian audience
3 | Social Sharing | Share Functionality | Native share API integration (mobile browsers share sheet) | P1 | Pending | V1.1 | Web | S
4 | Social Sharing | Share Functionality | Share count display (optional, can be vanity metric) | P2 | Pending | V1.2 | Web | M
5 | Social Sharing | Share Functionality | Text selection share (highlight text → share popup) | P2 | Pending | V1.2 | Web | M
Social Preview
6 | Social Sharing | Social Preview | Auto-generated social card images (og:image) with article title overlay | P1 | Pending | MVP | Web | M
7 | Social Sharing | Social Preview | Custom social card image upload per article | P1 | Pending | V1.1 | Web | S
8 | Social Sharing | Social Preview | Twitter Card preview in editor before publishing | P2 | Pending | V1.2 | Web | M
Distribution Channels
RSS & Syndication
9 | Distribution Channels | RSS & Syndication | Main RSS feed (all content) | P0 | Pending | MVP | Web | S
10 | Distribution Channels | RSS & Syndication | Per-category RSS feeds | P1 | Pending | V1.1 | Web | S
11 | Distribution Channels | RSS & Syndication | Per-author RSS feeds | P2 | Pending | V1.2 | Web | S
12 | Distribution Channels | RSS & Syndication | Full-text RSS (not truncated) for reader apps | P0 | Pending | MVP | Web | S
13 | Distribution Channels | RSS & Syndication | Google News sitemap submission | P0 | Pending | MVP | Web | M | Critical for news discovery
14 | Distribution Channels | RSS & Syndication | Apple News format export | P2 | Pending | V2 | Web | L
Social Auto-Posting
15 | Distribution Channels | Social Auto-Posting | Auto-post to Twitter/X on article publish (with custom text) | P1 | Pending | V1.1 | Web | M
16 | Distribution Channels | Social Auto-Posting | Auto-post to LinkedIn company page on publish | P1 | Pending | V1.1 | Web | M
17 | Distribution Channels | Social Auto-Posting | Auto-post to Telegram channel for breaking news | P1 | Pending | V1.2 | Web | M
18 | Distribution Channels | Social Auto-Posting | Social posting queue — schedule social shares at optimal times | P2 | Pending | V2 | Web | L
Content API & Embeds
19 | Distribution Channels | Content API & Embeds | Public content API (read-only) for partners and data consumers | P2 | Pending | V1.2 | API | L
20 | Distribution Channels | Content API & Embeds | Embeddable article widget (iframe snippet for partner sites) | P2 | Pending | V1.2 | Web | M
21 | Distribution Channels | Content API & Embeds | oEmbed support for article URLs | P2 | Pending | V2 | Web | M

## UX & Personalization
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Personalization
Following System
1 | Personalization | Following System | Follow categories — add to personalized feed | P1 | Pending | V1.1 | Web | M
2 | Personalization | Following System | Follow authors — add author's content to feed | P1 | Pending | V1.1 | Web | M
3 | Personalization | Following System | Follow tags/topics — fine-grained interest tracking | P2 | Pending | V1.2 | Web | M
4 | Personalization | Following System | "My Feed" page — personalized content based on follows | P1 | Pending | V1.1 | Web | L
5 | Personalization | Following System | Onboarding flow — select interests on first visit | P2 | Pending | V1.2 | Web | M
Reading Features
6 | Personalization | Reading Features | Bookmark / Save for Later (requires account) | P1 | Pending | V1.1 | Web | M
7 | Personalization | Reading Features | Reading history — recently read articles list | P1 | Pending | V1.1 | Web | M
8 | Personalization | Reading Features | "Continue reading" — resume from where you left off on long articles | P2 | Pending | V2 | Web | L
9 | Personalization | Reading Features | Bookmarks organized in collections/folders | P2 | Pending | V2 | Web | M
Reading Experience
Accessibility & Comfort
10 | Reading Experience | Accessibility & Comfort | Dark mode toggle (system preference + manual override) | P1 | Pending | V1.1 | Web | M
11 | Reading Experience | Accessibility & Comfort | Font size adjustment (S / M / L / XL) | P1 | Pending | V1.1 | Web | S
12 | Reading Experience | Accessibility & Comfort | Serif / sans-serif font toggle for articles | P2 | Pending | V1.2 | Web | S
13 | Reading Experience | Accessibility & Comfort | WCAG 2.1 AA compliance (contrast, keyboard nav, screen reader) | P0 | Pending | MVP | Web | L
14 | Reading Experience | Accessibility & Comfort | Reduced motion preference respect | P1 | Pending | MVP | Web | S
Comments & Discussion
15 | Reading Experience | Comments & Discussion | Comment section on articles (requires registered account) | P2 | Pending | V1.2 | Web | L
16 | Reading Experience | Comments & Discussion | Threaded replies (max 2 levels deep) | P2 | Pending | V1.2 | Web | M
17 | Reading Experience | Comments & Discussion | Comment moderation queue for editors | P2 | Pending | V1.2 | Web | M
18 | Reading Experience | Comments & Discussion | Comment upvote / helpful vote | P2 | Pending | V2 | Web | S
19 | Reading Experience | Comments & Discussion | Expert comment badge (verified medical professional comments) | P2 | Pending | V2 | Web | M | Trust differentiator
20 | Reading Experience | Comments & Discussion | Report comment for misinformation (healthcare-specific moderation) | P2 | Pending | V1.2 | Web | M | Patient safety — moderate medical claims

## Healthcare-Specific
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Medical Compliance
Disclaimer System
1 | Medical Compliance | Disclaimer System | Global medical disclaimer footer on every page | P0 | Pending | MVP | Web | S
2 | Medical Compliance | Disclaimer System | Category-specific disclaimers (patient content gets stronger disclaimer) | P0 | Pending | MVP | Web | S
3 | Medical Compliance | Disclaimer System | Article-level custom disclaimer override (for sensitive topics) | P1 | Pending | V1.1 | Web | S
4 | Medical Compliance | Disclaimer System | Emergency disclaimer — "If you are experiencing a medical emergency, call 112" | P0 | Pending | MVP | Web | S
5 | Medical Compliance | Disclaimer System | Drug information disclaimer — "Do not self-medicate based on this content" | P0 | Pending | MVP | Web | S
E-E-A-T Compliance
6 | Medical Compliance | E-E-A-T Compliance | Author expertise display on every article (credentials, specialization) | P0 | Pending | MVP | Web | S
7 | Medical Compliance | E-E-A-T Compliance | Medical reviewer badge with reviewer profile link | P0 | Pending | MVP | Web | S
8 | Medical Compliance | E-E-A-T Compliance | Source citations section with links to peer-reviewed studies | P0 | Pending | MVP | Web | M
9 | Medical Compliance | E-E-A-T Compliance | About Us page with editorial policy and medical review process | P0 | Pending | MVP | Web | S
10 | Medical Compliance | E-E-A-T Compliance | Editorial standards page — fact-checking, corrections policy | P0 | Pending | MVP | Web | S
11 | Medical Compliance | E-E-A-T Compliance | Corrections/updates log — transparent correction history per article | P1 | Pending | V1.1 | Web | M
Data Privacy (DPDP Act)
12 | Medical Compliance | Data Privacy (DPDP Act) | Cookie consent banner (DPDP Act / ePrivacy compliant) | P0 | Pending | MVP | Web | M
13 | Medical Compliance | Data Privacy (DPDP Act) | Privacy policy page with data processing details | P0 | Pending | MVP | Web | S
14 | Medical Compliance | Data Privacy (DPDP Act) | User data export (right to portability) | P1 | Pending | V1.1 | Web | M
15 | Medical Compliance | Data Privacy (DPDP Act) | Account deletion (right to erasure) | P1 | Pending | V1.1 | Web | M
16 | Medical Compliance | Data Privacy (DPDP Act) | No health data collection beyond reading preferences | P0 | Pending | MVP | Web | S | Platform is content-only, never collects patient health data
Healthcare Content Tools
Medical Terminology
17 | Healthcare Content Tools | Medical Terminology | Medical terminology tooltips — hover for plain-language explanation | P2 | Pending | V1.2 | Web | L
18 | Healthcare Content Tools | Medical Terminology | Glossary page — searchable medical terms dictionary | P2 | Pending | V1.2 | Web | M
19 | Healthcare Content Tools | Medical Terminology | ICD-10 code linking — inline references to diagnosis codes | P2 | Pending | V2 | Web | M
Interactive Health Widgets
20 | Healthcare Content Tools | Interactive Health Widgets | BMI calculator embed widget | P2 | Pending | V1.2 | Web | M
21 | Healthcare Content Tools | Interactive Health Widgets | Drug interaction checker link/embed (link to external tool) | P2 | Pending | V2 | Web | M
22 | Healthcare Content Tools | Interactive Health Widgets | Clinical trial search integration (link to CTRI/ClinicalTrials.gov) | P2 | Pending | V2 | Web | M
23 | Healthcare Content Tools | Interactive Health Widgets | CME quiz component — embed quiz at end of clinical articles | P2 | Pending | V2 | Web | L | Value-add for doctor audience
24 | Healthcare Content Tools | Interactive Health Widgets | Dosage calculator embed (with mandatory disclaimer) | P2 | Pending | V2 | Web | L
Health Awareness
25 | Healthcare Content Tools | Health Awareness | Health awareness calendar integration (WHO health days) | P1 | Pending | V1.1 | Web | M
26 | Healthcare Content Tools | Health Awareness | Disease outbreak tracking dashboard (link to IDSP/WHO data) | P2 | Pending | V2 | Web | L
27 | Healthcare Content Tools | Health Awareness | Vaccination schedule reference page (India NIS) | P2 | Pending | V2 | Web | M

## Analytics & Monetization
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Analytics
Traffic Analytics
1 | Analytics | Traffic Analytics | Page view tracking (privacy-respecting, e.g., Plausible/Fathom or GA4) | P0 | Pending | MVP | Web | M
2 | Analytics | Traffic Analytics | Unique visitor counts (daily, weekly, monthly) | P0 | Pending | MVP | Web | S
3 | Analytics | Traffic Analytics | Traffic source breakdown (organic, social, direct, referral, email) | P0 | Pending | MVP | Web | M
4 | Analytics | Traffic Analytics | Geographic distribution of readers | P1 | Pending | V1.1 | Web | S
5 | Analytics | Traffic Analytics | Device/browser breakdown | P1 | Pending | V1.1 | Web | S
Content Performance
6 | Analytics | Content Performance | Article performance dashboard: views, time on page, scroll depth, shares | P1 | Pending | V1.1 | Web | L
7 | Analytics | Content Performance | Category performance — views, engagement, growth per category | P1 | Pending | V1.1 | Web | M
8 | Analytics | Content Performance | Author performance — articles published, total views, avg engagement | P1 | Pending | V1.1 | Web | M
9 | Analytics | Content Performance | Top performing content report (last 7/30/90 days) | P1 | Pending | V1.1 | Web | M
10 | Analytics | Content Performance | Content decay report — articles with declining traffic (need refresh) | P2 | Pending | V1.2 | Web | M
11 | Analytics | Content Performance | Scroll depth tracking (how far readers actually read) | P1 | Pending | V1.1 | Web | M
A/B Testing
12 | Analytics | A/B Testing | A/B test headlines (show different headlines, measure CTR) | P2 | Pending | V1.2 | Web | L
13 | Analytics | A/B Testing | A/B test featured images | P2 | Pending | V2 | Web | M
14 | Analytics | A/B Testing | A/B test newsletter subject lines | P2 | Pending | V1.2 | Web | M
Monetization
Advertising
15 | Monetization | Advertising | Google AdSense integration (auto-placed display ads) | P1 | Pending | V1.1 | Web | M
16 | Monetization | Advertising | Direct ad sales management — sell ad slots to healthcare vendors | P2 | Pending | V1.2 | Web | L | Higher CPM than programmatic
17 | Monetization | Advertising | Ad placement zones: header banner, sidebar, in-article, footer | P1 | Pending | V1.1 | Web | M
18 | Monetization | Advertising | Ad-free experience for premium subscribers | P2 | Pending | V1.2 | Web | M
19 | Monetization | Advertising | Healthcare ad policy enforcement (no misleading health claims in ads) | P1 | Pending | V1.1 | Web | S | Editorial integrity
Sponsored Content
20 | Monetization | Sponsored Content | Sponsored article template with prominent 'Sponsored' badge | P1 | Pending | V1.1 | Web | M
21 | Monetization | Sponsored Content | Sponsored content disclosure (compliant with ASCI guidelines) | P1 | Pending | V1.1 | Web | S | ASCI compliance for Indian market
22 | Monetization | Sponsored Content | Sponsor dashboard — view metrics of their sponsored content | P2 | Pending | V1.2 | Web | L
23 | Monetization | Sponsored Content | Native advertising format (blends with editorial but clearly labeled) | P2 | Pending | V1.2 | Web | M
MedBrains HMS Lead Generation
24 | Monetization | MedBrains HMS Lead Generation | CTA banners on relevant articles (Hospital Leadership, Operations, Technology) | P0 | Pending | MVP | Web | S | Core business model — HMS lead gen
25 | Monetization | MedBrains HMS Lead Generation | Demo request form embedded in technology/operations articles | P0 | Pending | MVP | Web | M
26 | Monetization | MedBrains HMS Lead Generation | Lead attribution tracking — which article drove each demo request | P1 | Pending | V1.1 | Web | M
27 | Monetization | MedBrains HMS Lead Generation | MedBrains case study integration (embedded within relevant content) | P1 | Pending | V1.1 | Web | S
28 | Monetization | MedBrains HMS Lead Generation | Exit-intent popup for HMS demo on hospital admin-focused articles | P2 | Pending | V1.2 | Web | M
29 | Monetization | MedBrains HMS Lead Generation | Lead scoring — track content consumption for lead qualification | P2 | Pending | V2 | Web | L
30 | Monetization | MedBrains HMS Lead Generation | CRM integration (forward leads to sales pipeline) | P2 | Pending | V1.2 | Web | M
Affiliate & Partnerships
31 | Monetization | Affiliate & Partnerships | Affiliate link management (tracking, disclosure) | P2 | Pending | V1.2 | Web | M
32 | Monetization | Affiliate & Partnerships | Partner content hub — branded pages for sponsors/partners | P2 | Pending | V2 | Web | L
33 | Monetization | Affiliate & Partnerships | Webinar/event co-hosting with sponsors | P2 | Pending | V2 | Web | L
34 | Monetization | Affiliate & Partnerships | Revenue reporting dashboard (ads + sponsors + subscriptions + affiliates + leads) | P2 | Pending | V1.2 | Web | L

## Admin & Operations
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
CMS Administration
Dashboard
1 | CMS Administration | Dashboard | Admin dashboard — published today, scheduled, drafts in review, total articles | P0 | Pending | MVP | Web | M
2 | CMS Administration | Dashboard | Quick stats: total subscribers, page views today, trending articles | P1 | Pending | V1.1 | Web | M
3 | CMS Administration | Dashboard | Content pipeline view (articles by status across workflow stages) | P1 | Pending | V1.1 | Web | M
User & Role Management
4 | CMS Administration | User & Role Management | Roles: Super Admin, Editor-in-Chief, Section Editor, Writer, Medical Reviewer, Contributor | P0 | Pending | MVP | Web | M
5 | CMS Administration | User & Role Management | Invite writer / contributor by email | P0 | Pending | MVP | Web | M
6 | CMS Administration | User & Role Management | Per-category editor assignment (Section Editor for Technology, etc.) | P1 | Pending | V1.1 | Web | M
7 | CMS Administration | User & Role Management | Activity log — who published/edited/deleted what and when | P1 | Pending | V1.1 | Web | M
Content Operations
8 | CMS Administration | Content Operations | Bulk operations — bulk publish, bulk unpublish, bulk delete, bulk tag | P1 | Pending | V1.1 | Web | M
9 | CMS Administration | Content Operations | Content import — import from WordPress, Medium, Ghost (JSON) | P2 | Pending | V1.2 | Web | L
10 | CMS Administration | Content Operations | Content export — full backup as JSON/XML | P1 | Pending | V1.1 | Web | M
11 | CMS Administration | Content Operations | Media library — centralized image/file management | P0 | Pending | MVP | Web | M
12 | CMS Administration | Content Operations | Image upload with auto-compression and format conversion | P0 | Pending | MVP | Web | M
13 | CMS Administration | Content Operations | Scheduled content auto-publish (cron-based, timezone-aware) | P0 | Pending | MVP | Web | M
Infrastructure
Hosting & Deployment
14 | Infrastructure | Hosting & Deployment | Cloudflare Pages hosting (static frontend) | P0 | Pending | MVP | Web | M | Free tier, global CDN
15 | Infrastructure | Hosting & Deployment | Ghost CMS hosted instance (headless API mode) | P0 | Pending | MVP | Web | M | ~$30/month Ghost Pro or self-hosted
16 | Infrastructure | Hosting & Deployment | CI/CD pipeline — auto-deploy on push to main | P0 | Pending | MVP | Web | M
17 | Infrastructure | Hosting & Deployment | Staging environment for content preview before publish | P1 | Pending | V1.1 | Web | M
18 | Infrastructure | Hosting & Deployment | Automated daily backups (content + database) | P0 | Pending | MVP | Web | M
Monitoring
19 | Infrastructure | Monitoring | Uptime monitoring with alerts (UptimeRobot/Checkly) | P0 | Pending | MVP | Web | S
20 | Infrastructure | Monitoring | Error tracking (Sentry or similar) | P1 | Pending | V1.1 | Web | M
21 | Infrastructure | Monitoring | Performance monitoring — track Core Web Vitals in production | P1 | Pending | V1.1 | Web | M
22 | Infrastructure | Monitoring | CDN cache hit ratio monitoring | P2 | Pending | V1.2 | Web | S
Security
23 | Infrastructure | Security | SSL/TLS certificate (auto via Cloudflare) | P0 | Pending | MVP | Web | S
24 | Infrastructure | Security | DDoS protection (Cloudflare WAF) | P0 | Pending | MVP | Web | S
25 | Infrastructure | Security | Content Security Policy headers | P1 | Pending | MVP | Web | S
26 | Infrastructure | Security | Regular dependency vulnerability scanning | P1 | Pending | V1.1 | Web | S

## News & Breaking Coverage
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Indian Healthcare News
News Workflow
1 | Indian Healthcare News | News Workflow | Breaking news fast-publish workflow (skip medical review for news) | P1 | Pending | V1.2 | Web | M
2 | Indian Healthcare News | News Workflow | Breaking news banner on homepage (dismissible, auto-expire) | P1 | Pending | V1.2 | Web | M
3 | Indian Healthcare News | News Workflow | Priority alert email for breaking healthcare news | P1 | Pending | V1.2 | Web | M
4 | Indian Healthcare News | News Workflow | Push notification for breaking news (web push) | P2 | Pending | V1.2 | Web | M
5 | Indian Healthcare News | News Workflow | News article template — leaner than long-form, focus on facts + sources | P1 | Pending | V1.2 | Web | M
Policy & Government
6 | Indian Healthcare News | Policy & Government | Healthcare policy tracker page (active policies, pending bills, implementations) | P2 | Pending | V1.2 | Web | L
7 | Indian Healthcare News | Policy & Government | Ayushman Bharat / PMJAY scheme updates section | P1 | Pending | V1.2 | Web | M
8 | Indian Healthcare News | Policy & Government | ABDM (Ayushman Bharat Digital Mission) coverage — ABHA, health records | P1 | Pending | V1.2 | Web | M
9 | Indian Healthcare News | Policy & Government | NMC (National Medical Commission) regulatory updates | P1 | Pending | V1.2 | Web | M
10 | Indian Healthcare News | Policy & Government | NABH accreditation news and guideline changes | P1 | Pending | V1.2 | Web | M
11 | Indian Healthcare News | Policy & Government | Union Budget healthcare impact analysis (annual special coverage) | P2 | Pending | V1.2 | Web | M
12 | Indian Healthcare News | Policy & Government | State health policy tracker (key states: Maharashtra, Karnataka, TN, Kerala, Delhi) | P2 | Pending | V2 | Web | L
Industry News
13 | Indian Healthcare News | Industry News | Hospital industry news — mergers, expansions, new facilities | P1 | Pending | V1.2 | Web | M
14 | Indian Healthcare News | Industry News | Healthcare startup funding news | P1 | Pending | V1.2 | Web | M
15 | Indian Healthcare News | Industry News | Court ruling / legal update alerts (Supreme Court, NCDRC health rulings) | P2 | Pending | V1.2 | Web | M
16 | Indian Healthcare News | Industry News | Drug price regulation news (NPPA, DPCO updates) | P2 | Pending | V1.2 | Web | M
17 | Indian Healthcare News | Industry News | Medical education news (NEET, NEXT exam, new medical colleges) | P2 | Pending | V1.2 | Web | M
News Aggregation & Events
18 | Indian Healthcare News | News Aggregation & Events | PIB (Press Information Bureau) health news monitoring | P2 | Pending | V2 | Web | L
19 | Indian Healthcare News | News Aggregation & Events | MoHFW (Ministry of Health) press release tracking | P2 | Pending | V2 | Web | L
20 | Indian Healthcare News | News Aggregation & Events | Live blog for major events (HIMSS India, AHPI Conference, NABH events) | P2 | Pending | V1.2 | Web | L
21 | Indian Healthcare News | News Aggregation & Events | Event calendar — upcoming healthcare conferences, webinars, summits | P2 | Pending | V1.2 | Web | M
22 | Indian Healthcare News | News Aggregation & Events | News ticker / scrolling banner for latest updates | P2 | Pending | V2 | Web | M

## Mobile App (Future)
S.No | Module | Sub-Module | Feature | Priority | Status | Phase | Platform | Complexity | Notes
Mobile App (Native)
Core Reading
1 | Mobile App (Native) | Core Reading | Native article reader with optimized typography | P2 | Pending | V2 | Mobile | L
2 | Mobile App (Native) | Core Reading | Offline reading — download articles for offline access | P2 | Pending | V2 | Mobile | L
3 | Mobile App (Native) | Core Reading | Bookmarks sync with web account | P2 | Pending | V2 | Mobile | M
4 | Mobile App (Native) | Core Reading | Follow categories/authors/topics synced with web | P2 | Pending | V2 | Mobile | M
5 | Mobile App (Native) | Core Reading | Dark mode with OLED black option | P2 | Pending | V2 | Mobile | M
Notifications
6 | Mobile App (Native) | Notifications | Push notification for breaking news | P2 | Pending | V2 | Mobile | M
7 | Mobile App (Native) | Notifications | Push notification for followed author new article | P2 | Pending | V2 | Mobile | M
8 | Mobile App (Native) | Notifications | Notification preferences (category-level control) | P2 | Pending | V2 | Mobile | M
9 | Mobile App (Native) | Notifications | Silent/digest notification option (bundle into daily digest) | P2 | Pending | V2 | Mobile | M
Mobile-Specific
10 | Mobile App (Native) | Mobile-Specific | Share extension — share articles from other apps to bookmarks | P2 | Pending | V2 | Mobile | M
11 | Mobile App (Native) | Mobile-Specific | Widget — today's top 3 headlines on home screen | P2 | Pending | V2 | Mobile | M
12 | Mobile App (Native) | Mobile-Specific | Text-to-speech for articles (accessibility + commute listening) | P2 | Pending | V2 | Mobile | L
13 | Mobile App (Native) | Mobile-Specific | Haptic feedback on interactions | P2 | Pending | V2 | Mobile | S
14 | Mobile App (Native) | Mobile-Specific | App Store / Play Store listing optimization (ASO) | P2 | Pending | V2 | Mobile | M

## Content Categories Ref
# | Category Name | Target Audience | Content Types | Posting Frequency | Example Topics | Competitor Benchmarks | SEO Opportunity | Phase
1 | Hospital Leadership & Strategy | CEOs, CMOs, Hospital Admins, Board Members | Opinion pieces, Case studies, Interviews, Data analysis | 3-4/week | Hospital growth strategies, NABH prep, Financial management, Leadership interviews | Becker's Hospital Review, Healthcare Finance News | High | MVP
2 | Patient Education & Wellness | Patients, Families, Caregivers | Guides, How-tos, Explainers, Infographics, Q&A | 5-7/week | Disease guides, Wellness tips, Nutrition, Mental health, Pregnancy | Cleveland Clinic Health Essentials, Healthline, Mayo Clinic | Very High | MVP
3 | Doctor & Clinical Excellence | Doctors, Nurses, Clinical Staff | Clinical pearls, Evidence summaries, Expert opinions, CME | 3-4/week | Clinical guidelines, Case reports, Research updates, Drug updates | Medscape, NEJM Journal Watch, UpToDate Blog | High | MVP
4 | Operations & Efficiency | Hospital Managers, Dept Heads, COOs | How-to guides, Checklists, Templates, Benchmarks | 2-3/week | Process improvement, Supply chain, Staffing, Facility management | Becker's, Advisory Board, HFMA | Medium | MVP
5 | Technology & Innovation | CIOs, IT Managers, Health Tech Professionals | Product reviews, Analysis, Tutorials, Case studies | 3-5/week | AI in healthcare, EHR/EMR, Telemedicine, Cybersecurity, Interoperability | Healthcare IT News, HIMSS, MobiHealthNews | High | MVP
6 | Regulatory & Compliance | Compliance Officers, Legal Teams, Quality Heads | Analysis, Alerts, Checklists, Explainers | 2-3/week | NABH/JCI updates, NMC regulations, Legal rulings, DPDP Act, PCPNDT | Compliance Today (HCCA), Regulatory Focus | Medium | MVP
7 | Nursing & Allied Health | Nurses, Physiotherapists, Technicians | Practice guides, Career advice, Skill building, Research | 2-3/week | Nursing practice, Patient safety, Career growth, Skill workshops | American Nurse Journal, Nursing Times | Medium | V1.1
8 | Pharma Industry | Pharma Cos, Distributors, Drug Manufacturers | Industry news, Analysis, Market reports, Interviews | 3-4/week | Drug launches, Pricing policy, Supply chain, R&D pipeline, CDSCO updates | Pharma Times, ET Healthworld Pharma | High | V1.1
9 | Medical Devices & Equipment | Manufacturers, Biomedical Engineers, Procurement | Reviews, Buyer's guides, Regulatory, Innovation | 2-3/week | Device reviews, Procurement guides, CDSCO approvals, Innovation showcase | MedTech Dive, Medical Device Network | Medium | V1.1
10 | Health Insurance & TPA | Insurers, TPA Executives, Brokers | Policy analysis, Claim trends, Regulatory, Product reviews | 2/week | Policy analysis, Claim trends, IRDAI updates, New product launches | Insurance Journal, Policybazaar Blog | Medium | V1.2
11 | HealthTech & Startups | Founders, Investors, Digital Health Builders | Funding news, Product launches, Founder interviews, Market analysis | 3-4/week | Funding rounds, Product launches, Founder stories, Market maps | Rock Health, CB Insights Healthcare, YourStory Health | High | V1.2
12 | Medical Education & Research | Students, Academics, Researchers | Study guides, Research methods, Conference reports, Career advice | 2/week | NEET/NEXT prep, Residency guidance, Research methodology, Conference highlights | Student BMJ, Medical Education Online | Medium | V1.2
13 | Indian Healthcare News | All healthcare stakeholders | Breaking news, Policy updates, Court rulings, Budget analysis | Daily | Policy changes, ABDM updates, Hospital M&A, Court rulings, Budget impact | ET Healthworld, Mint Health, Business Standard Health | Very High | V1.2

## Tech Stack Reference
Layer | Technology | Purpose | Cost (Monthly) | Notes
CMS | Ghost (Headless) | Content management, newsletter, membership, API | $30 (Pro) or $5-10 (self-hosted) | Headless mode — API only, frontend decoupled
Frontend | Astro 5 | Static site generation, island architecture, fast performance | Free (SSG) | Content-first framework, 0 JS by default, partial hydration
Frontend UI | Tailwind CSS 4 | Utility-first styling for content pages | Free | Pairs well with Astro, great for content layout
Hosting | Cloudflare Pages | Static hosting with global CDN, edge functions | Free tier (unlimited sites) | Fast deploys, auto-SSL, DDoS protection included
Image CDN | Cloudflare Images / R2 | Image optimization, WebP/AVIF, responsive srcset | $5-10 | Or use Ghost built-in image processing
Search | Pagefind | Client-side static search (no server needed) | Free | Built into Astro, perfect for static sites
Analytics | Plausible / Fathom | Privacy-respecting page analytics | $9-14 | GDPR/DPDP compliant, no cookie consent needed
Newsletter | Ghost Built-in | Email newsletter with segmentation, automation | Included in Ghost | Up to 500 members free, scales with Ghost plan
Payments | Stripe (via Ghost) | Paid memberships, subscriptions | 2.9% + $0.30/tx | Ghost has native Stripe integration
Comments | Giscus / Cactus | Discussion system for articles | Free | GitHub-based (Giscus) or matrix-based (Cactus)
Forms | Formspree / Tally | Contact forms, demo request forms | Free tier | For MedBrains HMS lead capture forms
Monitoring | UptimeRobot | Uptime monitoring with alerts | Free (50 monitors) | 5-min check interval on free tier
Error Tracking | Sentry | Frontend error tracking | Free tier | Track JS errors in production
CI/CD | GitHub Actions | Build + deploy pipeline | Free (public repos) | Auto-deploy on push to main branch
DNS | Cloudflare DNS | DNS management, proxy | Free | Included with Cloudflare Pages
Email (Transactional) | Mailgun / Postmark | Transactional emails (welcome, password reset) | $0-15 | Only needed if Ghost email is insufficient
TOTAL ESTIMATED |  |  | $45-80/month | Scales to 100k+ monthly visitors before needing upgrades